VICHAKRA TECHNOLOGIES

Admin Panel & Client Portal

Full Build Plan  ·  MERN Stack  ·  Phase-Step-Wise  ·  Dependency Flow

Version 1.0  ·  Author: Rohith  ·  Date: 2026-04-11

Vichakra Technologies — Admin Panel & Client Portal

Full Build Plan · MERN Stack · Phase-Step-Wise · Dependency Flow

──────────────────────────────────────────────────────────────────────────────────────────

Architecture Overview

vichakra-platform/

├── client/          ← existing React site + new portal/admin pages

│   ├── src/

│   │   ├── pages/admin/       ← new admin pages

│   │   ├── pages/portal/      ← new client portal pages

│   │   ├── components/admin/  ← admin-specific components

│   │   ├── components/portal/ ← portal-specific components

│   │   ├── context/           ← AuthContext, ProjectContext

│   │   ├── hooks/             ← useAuth, useProjects, useFileUpload

│   │   └── api/               ← axios instance + API calls

└── server/          ← new Express + Node.js backend

├── src/

│   ├── routes/            ← auth, admin, client, projects, files

│   ├── controllers/       ← business logic

│   ├── models/            ← Mongoose schemas

│   ├── middleware/         ← auth guard, role check, upload

│   └── config/            ← db, env, cors, multer

└── uploads/               ← local file storage (dev)

Roles: admin (Vichakra team) · client (confirmed deal)

Auth: JWT access token (15m) + refresh token (7d), httpOnly cookie

File Storage: Multer (local dev) → Cloudinary or S3 (production)

Design System: Teal #0F766E, Outfit font, Tailwind CSS, Framer Motion, Lucide icons

──────────────────────────────────────────────────────────────────────────────────────────

Dependency Flow

Phase 0 (Foundation)

└── Phase 1 (Backend Auth)

└── Phase 2 (Frontend Auth + Login)

├── Phase 3 (Admin Core UI)

│       └── Phase 4 (Admin: Clients & Projects)

│               └── Phase 5 (Admin: Files & Status)

└── Phase 6 (Client Portal: Onboarding & Dashboard)

└── Phase 7 (Client Portal: Requirements)

└── Phase 8 (Client Portal: Feedback & Support)

└── Phase 9 (Integration & E2E Testing)

──────────────────────────────────────────────────────────────────────────────────────────

Phase 0 — Foundation & Monorepo Setup

Objectives

Establish the full project structure so all future phases have a stable base

Wire up local MongoDB, Express server, and connect to the existing React frontend

Scope

| In | Out |
| --- | --- |
| Monorepo folder setup (client/ + server/) | Cloud deployment config |
| Express app scaffold + CORS | Load balancing / reverse proxy |
| MongoDB connection (Mongoose) | Database seeding scripts |
| Environment variable setup (.env) | CI/CD pipelines |
| Axios instance in React with base URL | GraphQL / WebSockets |
| Proxy config in Vite for local dev |  |

Steps

Create server/ directory alongside client/ (existing repo root)

npm init in server, install: express, mongoose, dotenv, cors, bcryptjs, jsonwebtoken, multer, express-validator, morgan

Scaffold server/src/ — app.js, config/db.js, routes/index.js

Create .env with MONGO_URI, JWT_SECRET, JWT_REFRESH_SECRET, PORT, CLIENT_URL

Set up config/db.js — Mongoose connect with retry logic

Add vite.config.js proxy: /api → http://localhost:5000

Install axios in client, create src/api/axios.js with base URL + interceptors (auto-attach JWT, handle 401 refresh)

Add nodemon dev script, confirm server starts and DB connects

Risks & Constraints

Risk: MongoDB Atlas free tier has connection limits — use local MongoDB for dev, document Atlas setup separately

Risk: CORS misconfiguration will block all API calls — lock allowed origins to localhost:5173 in dev

Constraint: .env must never be committed — add to .gitignore immediately

What to Test

☐  `GET /api/health` returns `{ status: "ok" }` from Express

☐  Mongoose connects successfully (console log on startup)

☐  Vite proxy routes `/api/*` to Express without CORS errors

☐  Axios instance attaches `Authorization: Bearer <token>` header when token exists

──────────────────────────────────────────────────────────────────────────────────────────

Phase 1 — Backend Auth System

> Depends on: Phase 0 complete

Objectives

Build secure, role-aware JWT authentication on the server

Support admin and client roles with separate onboarding states

Scope

| In | Out |
| --- | --- |
| User model (Mongoose) | OAuth / social login |
| Register (admin-only action) | Email verification flow |
| Login → access + refresh tokens | 2FA |
| Refresh token rotation | Password strength meter |
| Logout (invalidate refresh token) | Account deletion |
| Auth middleware (verify JWT) |  |
| Role middleware (`requireAdmin`, `requireClient`) |  |
| First-login flag on User model |  |

Data Model — User

{

name: String,

email: String (unique),

password: String (hashed),

role: enum['admin', 'client'],

company: String,          // client only

phone: String,

avatar: String,           // URL

isFirstLogin: Boolean,    // default: true (client only)

isActive: Boolean,        // admin can deactivate

refreshToken: String,     // stored hashed

createdAt, updatedAt

}

Steps

Create models/User.js with schema above + pre-save bcrypt hook

Create controllers/authController.js:

register: Admin-only, creates client accounts, hashes password, returns new user (no token)

login: Validates credentials, issues access token (15m) + refresh token (7d), stores hashed refresh in DB

refresh: Validates refresh token, issues new access token

logout: Clears refresh token from DB + clears cookie

getMe: Returns current user from JWT

Create middleware/auth.js — protect (verify JWT), requireRole(...roles) (role guard)

Create routes/auth.js — wire routes with validation (express-validator)

Add global error handler middleware in app.js

Risks & Constraints

Risk: Storing refresh token in localStorage is XSS-vulnerable — store in httpOnly cookie; access token in memory (React state)

Risk: Token replay attacks on logout — always hash stored refresh tokens with bcrypt

Constraint: Only admins can create new user accounts — no public registration endpoint

What to Test

☐  `POST /api/auth/login` with valid credentials returns access token + sets httpOnly cookie

☐  `POST /api/auth/login` with wrong password returns 401

☐  Protected route returns 401 without token, 403 for wrong role

☐  `POST /api/auth/refresh` issues new access token from valid cookie

☐  `POST /api/auth/logout` clears cookie and invalidates DB refresh token

──────────────────────────────────────────────────────────────────────────────────────────

Phase 2 — Frontend Auth + Login Page

> Depends on: Phase 1 complete

Objectives

Build the login page that visually matches the existing site

Implement AuthContext with token refresh, protected routes, and role-based redirects

Scope

| In | Out |
| --- | --- |
| Login page (`/login`) | Forgot password / OTP |
| AuthContext (React Context) | Remember me (persistent sessions beyond 7d) |
| `useAuth` hook | Account settings page |
| `ProtectedRoute` component (role-aware) |  |
| Auto-refresh on 401 (Axios interceptor) |  |
| Redirect after login by role |  |

UI Design (consistent with existing site)

Background: bg-hero-gradient + bg-dot-grid (same as HomePage hero)

Card: premium-card centered, max-width md, with glass morphism

Brand: circular logo + "Vichakra Technologies" heading

Input: .input-field class (already defined in index.css)

Button: <Button variant="primary" size="lg"> (existing component)

Animation: fadeUp on mount via Framer Motion

Error states: red-500 inline messages

Steps

Create src/context/AuthContext.jsx — stores user, accessToken (in-memory), loading; exposes login(), logout(), refreshToken()

Create src/hooks/useAuth.js — consumes AuthContext

Update src/api/axios.js — request interceptor attaches token; response interceptor handles 401 → silent refresh → retry

Create src/components/auth/ProtectedRoute.jsx — checks auth + role, redirects accordingly:

Unauthenticated → /login

admin → /admin

client → /portal

Create src/pages/auth/LoginPage.jsx — form with email + password, calls login(), shows loading state

Update App.jsx — wrap with <AuthProvider>, add routes:

/login → LoginPage

/admin/* → ProtectedRoute (role: admin) → AdminLayout

/portal/* → ProtectedRoute (role: client) → PortalLayout

Risks & Constraints

Risk: Access token stored in React state is lost on page refresh — on app load, silently call /api/auth/refresh to restore session from cookie

Risk: Flash of unauthenticated content on refresh — show full-screen loading spinner while auth is restoring

Constraint: Login page must not share Navbar/Footer with main site — use a separate layout

What to Test

☐  Login with admin credentials redirects to `/admin`

☐  Login with client credentials redirects to `/portal`

☐  Navigating to `/admin` while unauthenticated redirects to `/login`

☐  Page refresh retains session (silent refresh from cookie works)

☐  Wrong credentials shows inline error, not alert

☐  Logout clears state and redirects to `/login`

──────────────────────────────────────────────────────────────────────────────────────────

Phase 3 — Admin Panel: Core Layout & Dashboard

> Depends on: Phase 2 complete

Objectives

Build the admin shell layout (sidebar + header)

Build the overview dashboard with live stats

Scope

| In | Out |
| --- | --- |
| Admin sidebar (collapsible) | Multi-admin permissions/roles |
| Admin header with profile + logout | Audit logs |
| Dashboard stats (clients, projects, open items) | Analytics charts (deferred to later) |
| Responsive layout | Theme switcher |

UI Design

Sidebar: bg-gray-950 (same as Footer), teal accent for active nav item, Lucide icons

Header: bg-white with bottom border, admin avatar + name + logout button

Stats cards: StatCard component (already exists), gradient text for numbers

Layout: fixed sidebar (240px) + scrollable main content area

Consistent with site: Outfit font, #0F766E accent, premium-card for content areas

Steps

Create src/pages/admin/ directory

Create src/components/admin/AdminLayout.jsx — sidebar + header shell, outlet for child pages

Create src/components/admin/AdminSidebar.jsx — nav links: Dashboard, Clients, Projects, Files, Status, Settings

Create src/components/admin/AdminHeader.jsx — title area + admin profile dropdown

Create src/pages/admin/DashboardPage.jsx — fetch summary stats from /api/admin/stats:

Total clients, active projects, pending reviews, files stored

Recent activity feed (last 5 actions)

Create GET /api/admin/stats endpoint on server

Risks & Constraints

Risk: Sidebar z-index conflicts with modals on mobile — use portal-based modals

Constraint: All /api/admin/* routes must be gated by protect + requireRole('admin') middleware

What to Test

☐  Admin sidebar renders all nav items with correct icons

☐  Active route is highlighted in sidebar

☐  Dashboard stats load from API (not hardcoded)

☐  Sidebar collapses to icon-only on small screens

☐  Logout from header clears session correctly

──────────────────────────────────────────────────────────────────────────────────────────

Phase 4 — Admin Panel: Client & Project Management

> Depends on: Phase 3 complete

Objectives

Give admins full CRUD over clients and projects

Link projects to clients; support milestones and status

Scope

| In | Out |
| --- | --- |
| Client list + add/edit/deactivate | Bulk import clients (CSV) |
| Client detail view | Client billing/invoicing |
| Project CRUD | Gantt chart view |
| Milestone management per project | Time tracking |
| Assign project to client |  |
| Project status: Draft→Active→Review→Delivered→Closed |  |

Data Models

Project:

{

title: String,

description: String,

client: ObjectId (ref: User),

status: enum['draft','active','in-review','delivered','closed'],

milestones: [{ title, dueDate, completed: Boolean }],

demoLinks: [{ label, url }],

attachments: [ObjectId (ref: File)],

notes: String,           // internal admin-only notes

startDate, endDate,

createdAt, updatedAt

}

Client Profile (extension of User):

{

// stored in User model

company: String,

industry: String,

projectsAssigned: [ObjectId (ref: Project)]

}

Steps

Create models/Project.js with schema above

Create controllers/adminController.js — client CRUD, project CRUD

Create routes: GET/POST /api/admin/clients, PUT/DELETE /api/admin/clients/:id, same pattern for projects

Build src/pages/admin/ClientsPage.jsx — table with search/filter, "Add Client" modal (creates User with role: client, generates temp password)

Build src/pages/admin/ClientDetailPage.jsx — client info + linked projects list

Build src/pages/admin/ProjectsPage.jsx — project cards with status badges, filter by status/client

Build src/pages/admin/ProjectDetailPage.jsx — milestone checklist, demo link manager, status dropdown, notes textarea

Build reusable src/components/admin/StatusBadge.jsx — color-coded status pill

Risks & Constraints

Risk: Admins accidentally deactivating a client mid-project — show warning modal if client has active projects

Risk: Temp passwords sent in response (not email) during dev — flag clearly in UI to change method before production

Constraint: Project deletion should be soft-delete only (mark isDeleted: true) to preserve client history

What to Test

☐  Create client → user appears in DB with role: `client` and `isFirstLogin: true`

☐  Create project + assign to client → client can see it in portal (Phase 6 verification)

☐  Milestone toggle (complete/incomplete) persists on refresh

☐  Project status change updates immediately in both admin and client views

☐  Deactivated client cannot log in

──────────────────────────────────────────────────────────────────────────────────────────

Phase 5 — Admin Panel: File Management & Status Updates

> Depends on: Phase 4 complete

Objectives

Allow admins to upload, organize, and attach files to projects or clients

Allow admins to broadcast status updates visible to clients

Scope

| In | Out |
| --- | --- |
| File upload (Multer) with type/size validation | Video streaming |
| File browser per project | CDN integration |
| Attach/detach files from projects | Folder hierarchy |
| Global status announcements | Email notifications |
| Per-project status notes for client | Push notifications |

Data Model — File

{

filename: String,

originalName: String,

mimetype: String,

size: Number,

path: String,            // local path (dev) / cloud URL (prod)

uploadedBy: ObjectId (ref: User),

project: ObjectId (ref: Project),

isPublic: Boolean,       // client-visible or internal only

createdAt

}

Data Model — StatusUpdate

{

title: String,

message: String,

type: enum['info','success','warning'],

project: ObjectId (ref: Project),   // null = global

createdBy: ObjectId (ref: User),

createdAt

}

Steps

Create models/File.js and models/StatusUpdate.js

Configure middleware/upload.js — Multer: 10MB limit, allowed types: jpg/png/pdf/zip/mp4/doc/xlsx

Create file routes: POST /api/admin/files/upload, GET /api/admin/files, DELETE /api/admin/files/:id

Create status routes: POST/GET /api/admin/status-updates, DELETE /api/admin/status-updates/:id

Build src/pages/admin/FilesPage.jsx — drag-and-drop upload zone (<input type="file">), file grid with preview thumbnails, attach-to-project selector

Build src/pages/admin/StatusUpdatesPage.jsx — compose update form, list of sent updates, project selector (or global)

Add file section to ProjectDetailPage.jsx — show attached files, toggle isPublic

Risks & Constraints

Risk: Large file uploads blocking the event loop — use streaming uploads with Multer

Risk: Public files accidentally exposing internal documents — isPublic: false by default; require explicit toggle

Constraint: File storage path must be configurable via env var for easy switch to cloud storage

What to Test

☐  Upload a 5MB PDF → file appears in file browser with correct metadata

☐  Upload beyond 10MB → rejected with clear error message

☐  Toggle file `isPublic` → client sees/doesn't see file in portal

☐  Post a global status update → appears in all client dashboards

☐  Post a project-specific update → only appears for that project's client

☐  Delete a file → removed from DB and disk

──────────────────────────────────────────────────────────────────────────────────────────

Phase 6 — Client Portal: Onboarding & Dashboard

> Depends on: Phase 2 (Auth) + Phase 4 (Projects exist)

Objectives

First-time client experience with tutorial overlay

Client dashboard showing their project(s), progress, and updates

Scope

| In | Out |
| --- | --- |
| Client portal shell layout | Multiple client accounts per company |
| First-login tutorial (step-by-step overlay) | Video walkthrough |
| Dashboard: active projects, progress, recent updates | Billing history |
| Project progress bar (% milestones complete) | Calendar view |
| Demo link viewer |  |
| Status updates feed |  |

UI Design

Layout: minimal sidebar (Home, My Project, Requirements, Support, Feedback) + header

Color: same teal brand, premium-card for sections, clean white backgrounds

Tutorial: full-screen step overlay with dark backdrop, fadeIn animation, "Next / Got it" buttons

Progress: segmented milestone bar, teal fill, gray empty segments

Welcome message: "Welcome, [Name]" with company name

Steps

Create src/pages/portal/ directory

Create src/components/portal/PortalLayout.jsx — slim sidebar + header, client-specific nav

Create src/components/portal/OnboardingTutorial.jsx — multi-step overlay (5 steps: Welcome → My Project → Requirements → Support → Done), stored completion in User.isFirstLogin

Create src/pages/portal/PortalDashboardPage.jsx:

Fetch client's projects from GET /api/portal/projects

Display project status, milestone progress bar, recent status updates

Demo links section (if any published)

Create GET /api/portal/projects (client-scoped: only returns their projects)

Create GET /api/portal/status-updates (returns global + their project updates)

PATCH /api/portal/onboarding-complete — sets isFirstLogin: false

Risks & Constraints

Risk: Client sees projects from other clients — all portal queries MUST filter by req.user._id or project's client field

Risk: Tutorial re-appearing on every login if isFirstLogin update fails silently — add error handling and retry

Constraint: If client has no active project yet (deal confirmed but project not created), show a friendly empty state — not an error

What to Test

☐  First login triggers tutorial overlay

☐  Second login does NOT show tutorial

☐  Client only sees their own projects (not others)

☐  Milestone completion % calculates correctly

☐  Demo links open in new tab

☐  Status update feed shows both global and project-specific updates

☐  Empty state renders correctly when no project assigned yet

──────────────────────────────────────────────────────────────────────────────────────────

Phase 7 — Client Portal: Requirements Submission

> Depends on: Phase 6 complete

Objectives

Allow clients to submit their full project vision: text, reference images, files, and structured answers

Admin can view submissions inside the project detail

Scope

| In | Out |
| --- | --- |
| Multi-step requirements form | Real-time collaborative editing |
| Text fields: vision, goals, preferences | AI-generated requirement parsing |
| Image/file uploads (reference material) | Version history of requirements |
| Progress save (draft) |  |
| Admin view of client submissions |  |
| Submission lock after first submit (edit-request flow) |  |

Data Model — Requirements

{

project: ObjectId (ref: Project),

client: ObjectId (ref: User),

vision: String,                   // "What do you want to build?"

targetAudience: String,

goals: [String],                  // list of specific goals

designPreferences: {

style: String,                  // minimal, bold, playful, etc.

colorPreference: String,

referenceWebsites: [String]

},

features: [String],               // requested feature list

files: [ObjectId (ref: File)],    // reference images, brand assets

additionalNotes: String,

status: enum['draft','submitted','acknowledged'],

submittedAt: Date

}

Steps

Create models/Requirements.js

Create portal routes: POST /api/portal/requirements, GET /api/portal/requirements/:projectId, PATCH /api/portal/requirements/:id (draft save)

Create admin route: GET /api/admin/projects/:id/requirements (view client submission)

Build src/pages/portal/RequirementsPage.jsx — multi-step form (4 steps):

Step 1: Vision — textarea for description + target audience

Step 2: Design — style preference selector (visual cards), color input, reference URLs

Step 3: Features — tag-based feature input (type + add to list)

Step 4: Files — drag-and-drop multi-file upload for reference images/brand assets

Add "Save Draft" auto-save (debounced) + "Submit" button (locks form)

Add requirements tab in src/pages/admin/ProjectDetailPage.jsx — read-only view of submission

Admin can mark requirements as "Acknowledged" — updates status + shows confirmation to client

Risks & Constraints

Risk: Large reference image uploads (5+ images) — implement client-side compression for images before upload, or enforce 5MB per file

Risk: Client submits incomplete requirements — enforce minimum field completion before enabling "Submit" (Step completion indicators)

Constraint: After submission, form becomes read-only; any changes require client to message support (handled in Phase 8)

What to Test

☐  Draft saves automatically without page reload

☐  Refreshing the page restores draft

☐  All 4 steps must have minimum data before "Submit" is enabled

☐  After submit, form fields become read-only

☐  Admin sees submitted requirements in project detail

☐  File uploads within requirements attach to the correct project

☐  "Acknowledged" status update visible to client

──────────────────────────────────────────────────────────────────────────────────────────

Phase 8 — Client Portal: Feedback, Support & Post-Project

> Depends on: Phase 7 complete

Objectives

Allow clients to submit feedback at any project stage

Allow clients to request guidance/assistance after project completion

Give clients a simple way to reach Vichakra

Scope

| In | Out |
| --- | --- |
| Project feedback form (rating + comments) | Full chat / messaging system |
| Post-project support ticket system | SLA tracking |
| "Approach Us" contact form in portal | Live chat widget |
| Support ticket list (client view) | Admin ticket queue UI (use email for now) |
| Admin can view all feedback |  |

Data Models

Feedback:

{

project: ObjectId (ref: Project),

client: ObjectId (ref: User),

rating: Number (1-5),

communication: Number (1-5),

quality: Number (1-5),

timeliness: Number (1-5),

comments: String,

isPublic: Boolean,              // admin can make testimonial-worthy feedback public

createdAt

}

SupportTicket:

{

client: ObjectId (ref: User),

project: ObjectId (ref: Project),   // optional, null for pre-project

subject: String,

message: String,

category: enum['guidance','bug','change-request','general'],

status: enum['open','in-progress','resolved'],

adminResponse: String,

createdAt, updatedAt

}

Steps

Create models/Feedback.js and models/SupportTicket.js

Create portal routes: POST /api/portal/feedback, GET /api/portal/feedback/:projectId

Create support routes: POST /api/portal/support, GET /api/portal/support (client's tickets), PATCH /api/admin/support/:id (admin responds)

Build src/pages/portal/FeedbackPage.jsx — star rating inputs (5 criteria) + comments textarea; show existing feedback if already submitted

Build src/pages/portal/SupportPage.jsx — ticket list + "New Request" form with category selector; show admin response inline when resolved

Build "Approach Us" section in PortalDashboardPage.jsx — quick contact form (even before project assignment)

Add src/pages/admin/FeedbackPage.jsx — all feedback table, rating averages, toggle isPublic

Add feedback + support tabs in admin ProjectDetailPage.jsx

Risks & Constraints

Risk: Clients submitting feedback before project is complete — allow feedback only when project status is delivered or closed; show guidance message otherwise

Risk: Support ticket volume overwhelming without a queue — notify admin via console log + email (nodemailer) for now; proper queue is post-MVP

Constraint: Admin responses are plain text only (no rich text editor) to keep Phase 8 scope tight

What to Test

☐  Feedback form only appears for `delivered`/`closed` projects

☐  Rating 1-5 persists and displays correctly

☐  Client cannot submit feedback twice (form hides after submission)

☐  Support ticket appears in admin view immediately after submission

☐  Admin response updates ticket status and is visible to client

☐  "Approach Us" form submits even without an active project

──────────────────────────────────────────────────────────────────────────────────────────

Phase 9 — Integration, Hardening & E2E Testing

> Depends on: All phases complete

Objectives

Connect all moving parts end-to-end

Harden security, validate edge cases, fix integration bugs

Ensure UI is pixel-consistent with existing site on all screen sizes

Scope

| In | Out |
| --- | --- |
| Full end-to-end user journey testing | Automated test suite (jest/cypress) |
| Input sanitization (server-side) | Performance profiling |
| Rate limiting on auth endpoints | SEO for portal/admin pages |
| HTTP security headers (helmet.js) |  |
| Responsive QA: mobile, tablet, desktop |  |
| Error boundary in React |  |
| 404 and error pages for portal/admin |  |
| Environment variable audit |  |

Steps

Install helmet, express-rate-limit on server — configure security headers + limit /api/auth/login to 10 req/15min per IP

Add express-mongo-sanitize to prevent NoSQL injection

Add React <ErrorBoundary> wrapper in AdminLayout and PortalLayout

Build src/pages/NotFoundPage.jsx and src/pages/ErrorPage.jsx styled to match site

Audit all API responses — ensure no passwords/tokens leak in any response body

Run full user journey manually:

Admin creates client → client receives credentials → client logs in → sees tutorial → submits requirements → admin views → marks acknowledged → updates project milestones → client sees progress → project delivered → client submits feedback → admin views feedback

Test all modals, forms, and file uploads on mobile (375px) and tablet (768px)

Verify all protected routes reject unauthorized access

Check all .env references work and document required variables in server/README.md

Risks & Constraints

Risk: Integration bugs between phases discovered late — mitigate by running cross-phase checks at end of each phase (not just Phase 9)

Risk: File paths breaking on different OS (Windows backslash vs Unix forward slash) — use path.join() everywhere

Constraint: No deploy config in this plan (per user instruction) — ensure all code works with npm run dev locally

What to Test

☐  Full client lifecycle: create → login → requirements → progress → feedback

☐  Admin can manage clients, projects, files, and status updates without errors

☐  No 500 errors on any standard user action

☐  All forms reject empty/invalid inputs with helpful messages

☐  Auth tokens expire correctly and session restores on refresh

☐  Mobile layout: sidebar collapses, forms are usable, touch targets are adequate

☐  No `console.error` warnings in browser during normal flows

──────────────────────────────────────────────────────────────────────────────────────────

Quick Reference: New Routes

Server Routes

| Method | Path | Role | Description |
| --- | --- | --- | --- |
| POST | `/api/auth/login` | public | Login |
| POST | `/api/auth/refresh` | public | Refresh token |
| POST | `/api/auth/logout` | auth | Logout |
| GET | `/api/auth/me` | auth | Current user |
| GET | `/api/admin/stats` | admin | Dashboard stats |
| GET/POST | `/api/admin/clients` | admin | List / create clients |
| PUT/DELETE | `/api/admin/clients/:id` | admin | Edit / deactivate client |
| GET/POST | `/api/admin/projects` | admin | List / create projects |
| PUT/DELETE | `/api/admin/projects/:id` | admin | Edit / delete project |
| GET | `/api/admin/projects/:id/requirements` | admin | View requirements |
| POST | `/api/admin/files/upload` | admin | Upload file |
| GET/DELETE | `/api/admin/files/:id` | admin | Browse / delete file |
| GET/POST | `/api/admin/status-updates` | admin | Manage status updates |
| GET | `/api/admin/feedback` | admin | All feedback |
| PATCH | `/api/admin/support/:id` | admin | Respond to ticket |
| GET | `/api/portal/projects` | client | Their projects |
| GET | `/api/portal/status-updates` | client | Status feed |
| PATCH | `/api/portal/onboarding-complete` | client | Mark tutorial done |
| GET/POST/PATCH | `/api/portal/requirements` | client | Requirements CRUD |
| POST/GET | `/api/portal/feedback` | client | Submit / view feedback |
| POST/GET | `/api/portal/support` | client | Support tickets |

Client React Routes

| Path | Component | Role |
| --- | --- | --- |
| `/login` | LoginPage | public |
| `/admin` | Admin Dashboard | admin |
| `/admin/clients` | Clients List | admin |
| `/admin/clients/:id` | Client Detail | admin |
| `/admin/projects` | Projects List | admin |
| `/admin/projects/:id` | Project Detail | admin |
| `/admin/files` | File Manager | admin |
| `/admin/status` | Status Updates | admin |
| `/admin/feedback` | Feedback Viewer | admin |
| `/portal` | Portal Dashboard | client |
| `/portal/requirements` | Requirements Form | client |
| `/portal/support` | Support Tickets | client |
| `/portal/feedback` | Feedback Form | client |

──────────────────────────────────────────────────────────────────────────────────────────

NPM Packages to Install

Server

npm install express mongoose dotenv cors bcryptjs jsonwebtoken multer express-validator morgan helmet express-rate-limit express-mongo-sanitize

npm install -D nodemon

Client (additions to existing)

npm install axios

──────────────────────────────────────────────────────────────────────────────────────────

*Plan version: 1.0 · Author: Rohith · Date: 2026-04-11*